## Sprint 1
Developers | Initials | Hours Available | Hours Left | Tasks | Developer | Hours | Hours Worked | Hours Left | Priority (1-10)
John Brock | JB | 30 | -8 | Set up a PhoneGap environment for the Android platform. | All |  |  |  | 10
Ryan Oji | RO | 30 | 0 |  | CS | 1 | 1 | 0
Clarissa Soon | CS | 30 | -8 |  | JB | 1 | 1 | 0
Irma Lam | IL | 30 | -3 |  | RO | 1 | 0 | 1
[5 empty] | IL | 1 | 1 | 0
0
|  |  |  | Creation of a Heroku server | JB |  |  | 0 | 10
|  |  |  | Set up database | JB | 3 | 5 | -2 |  | Task that was not planned to be performed by this developer
|  |  |  | Set up database | IL | 3 | 5 | -2 |  | Task that was not needed
|  |  |  | Set up database | CS | 3 | 5 | -2 |  | Task moved to the backlog
|  |  |  | Set up repository | JB | 2 | 3 | -1
|  |  |  | Set up a connection between the web server and phone. |  |  |  | 0 | 10
[5 empty] | JB | 5 | 0 | 5
[5 empty] | CS | 5 | 5 | 0
|  |  |  | UI - Design |  |  |  | 0
|  |  |  | Prototype | RO | 2 | 2 | 0
|  |  |  | Creation of accounts | CS |  |  | 0 | 7
|  |  |  | Retrieve the user's phone number | CS | 0.5 | 0 | 0.5 | Not needed
|  |  |  | Get account creation information from UI | CS | 3.5 | 5 | -1.5
|  |  |  | Add to database | CS | 3 | 4 | -1
|  |  |  | Integration | CS | 3 | 3 | 0
|  |  |  | Integration | RO | 2 | 0 | 2
|  |  |  | Unit Test | CS | 5 | 0 | 5
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | CS | 1 | 0 | 1
|  |  |  | UI - Account creation menu | RO |  |  | 0 | 7
|  |  |  | User information (name, email address, username, password) | RO | 2 | 0 | 2
|  |  |  | User information (name, email address, username, password) | IL | 2 | 3 | -1
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | RO | 1 |  | 1
|  |  |  | Account login |  |  |  | 0 | 5
|  |  |  | Check the database for correct username and password | CS | 2 | 5 | -3
|  |  |  | Integration | CS | 3 | 3 | 0
|  |  |  | Integration | RO | 2 | 0 | 2
|  |  |  | Unit Test | CS | 5 | 0 | 5
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | CS | 1 | 0 | 1
|  |  |  | UI - Login menu | RO |  |  | 0 | 7
|  |  |  | Username and password form | RO | 1 | 0 | 1
|  |  |  | Username and password form | IL | 1 | 3 | -2
|  |  |  | Forgotten password | RO | 0.5 | 0 | 0.5
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | RO | 1 | 0 | 1
|  |  |  | Upload a file from phone to account |  |  |  | 0 | 8
|  |  |  | Store file in S3 server | JB | 4 | 5 | -1
|  |  |  | Write to database (linked to account's information) | JB | 3 | 4 | -1
|  |  |  | Integration | JB | 2 | 2 | 0
|  |  |  | Integration | RO | 2 | 0 | 2
|  |  |  | Unit Test | JB | 3 | 0 | 3
|  |  |  | Code Review | CS | 1 | 0 | 1
0
|  |  |  | Contact selection to choose who to share a file with |  |  |  |  | 8
|  |  |  | Read from database to retrieve contacts | IL | 4 | 4 | 0
|  |  |  | Push notifications/text messages to receiver | IL | 3 | 0 | 3
|  |  |  | Integration | IL | 3 | 3 | 0
|  |  |  | Integration | RO | 3 | 0 | 3
|  |  |  | Unit Test | IL | 3 | 0 | 3
|  |  |  | Code Review | CS | 1 | 0 | 1
|  |  |  | Code Review | IL | 1 | 0 | 1
|  |  |  | Share files with other users |  |  |  |  | 8
|  |  |  | Receive confirmation | IL | 3 | 0 | 3
|  |  |  | Copy file to receiver's account (if accepted) | IL | 5 | 0 | 5
|  |  |  | Receive confirmation | JB | 3 | 3 | 0
|  |  |  | Copy file to receiver's account (if accepted) | JB | 5 | 5 | 0
|  |  |  | Integration | IL | 3 | 3 | 0
|  |  |  | Integration | RO | 3 | 0 | 3
|  |  |  | Unit Test | IL | 3 | 0 | 3
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | IL | 1 | 0 | 1
|  |  |  | UI - Contacts menu |  |  |  |  | 7
|  |  |  | Simple UI | RO | 2.5 | 2.5 | 0
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | RO | 1 | 0 | 1
|  |  |  | UI - Files menu |  |  |  |  | 7
|  |  |  | Simple UI | RO | 2 | 2 | 0
|  |  |  | Code Review | JB | 1 | 0 | 1
|  |  |  | Code Review | RO | 1 | 0 | 1
|  |  |  | UI - Drag and drop function |  |  |  |  | 7
|  |  |  | Simple UI | RO | 3 | 0 | 3
|  |  |  | Code Review | IL | 1 | 0 | 1
|  |  |  | Code Review | RO | 1 | 0 | 1

## Product Backlog
PRODUCT BACKLOG | Priority
Save files from server to phone | 2
Delete files from my account | 6
View account files on application | 4
Add or delete someone to or from contact list | 4 | remove from backlog
Receive push notifications when someone wants to share a file | 3
Accept or decline file sharing requests | 3
Receive confirmation of a successful/unsuccessful file transfer | 3
UI - Login menu
Forgotten password
Drag and Drop functionality